VOLUME 2

SECTION 3

SPECIAL CONDITIONS

- CONTENTS

- These conditions amplify and supplement the General Conditions governing the Contract. Unless the Special Conditions provide otherwise, the General Conditions remain fully applicable. The numbering of the Articles of the Special Conditions is not consecutive but follows the numbering of the General Conditions. Other Special Conditions should be indicated afterwards.

Article 2	Language of the Contract

2.1	The language used shall be English.

Article 4	Communication

4.1	Petrovic Miodrag, municipality Niska Banja

Petrovic018@gmail.com

Article 5	Supervisor and Supervisor’s representative

5.2	Supervisor will be selected before start date of works implementation

Article 9	Access to the site

9.1	The Contractor is reminded that there is a Head of Delegation of the European Commission in the state of the Contracting Authority. The Contractor is obliged to give the Head of Delegation free access to its sites, factories, workshops, etc., and generally assist the Head of Delegation, like the project Supervisor, in the performance of his duties. The same provisions also apply to the appointed representatives of the Head of Delegation.

Article 12	General Obligations

12.9	Specify the specific activities to be put in place by the Contractor to comply with its minimum obligation toward visibility. These activities must comply with the rules lay down in the Communication and Visibility Manual for EU External Actions published by the European Commission.

Article 15	Performance guarantee

15.1	By derogation to Article 15 of the General Conditions, no performance guarantee is required under this contract.

Article 16	Liabilities and Insurance

16.1 a)	By way of derogation from Article 16.1, a) paragraph 2, of the general conditions, compensation for damage to the works resulting from the Contractor's liability in respect of the Contracting Authority is capped at an amount equal to the 5% of contract value. Or it will be paid off if Contractor provide financial guarantee for that amount(bank guarantee/promissory note/etc).

Article 17	Programme of implementation of tasks

17.1	The Contractor shall provide the Supervisor with a simplified programme of implementation of the tasks. This programme shall include at least the order and time limits in which the Contractor proposes to carry out the works, and shall be based on the tranches foreseen in art. 49.1 of the special conditions.

17.2. 	The Supervisor shall return this document to the Contractor with any relevant remarks within 10 days of receipt, save where the Supervisor, within those 10 days, notifies the Contractor of its wish for a meeting in order to discuss the documents submitted.

Article 21	Exceptional risks

21.4	No potential risks

Article 34	Period of implementation of tasks

34.1	6 months from commencing date

Article 39	Work register

39.1	Work registry is not mandatory.

Article 40	Origin and quality of works and materials

## 40.1	The goods to be purchased may originate from any country, whenever the total price of the estimated quantity of those goods, as reflected in a separate item of the Breakdown of the Lump-sum Price (Volume 4.2.3) is below 100.000 €. A category of similar goods to be purchased shall not be broken down over more than 1 item of the Breakdown of the Lump-sum Price (Volume 4.2.3)]

## For these purposes, ‘origin’ means the place where the goods are mined, grown, produced or manufactured and/or from which services are provided. The origin of the goods must be determined according to the EU Customs Code or the applicable international agreement.

Article 43	Ownership of plant and materials

43.2	The equipment, temporary structures, plant and materials on the site shall for the duration of the execution of the works, be vested in the Contracting Authority.

Article 44:	General principles for payments

44.1	Payments shall be made in RSD in exchange rate Infor Euro for month when invoice is issued.

Article 46	Pre-financing

46.1	The only prefinancing granted to the Contractor, is the lump sum advance referred to in Article 46.1(a).

Article 47	Retention monies

47.1	The sum retained to guarantee implementation of the Contractor’s obligations during the defects liability period is 5 % of the contract price. By derogation to Article 47.1 of the General Conditions, that money is not retained from interim payments. The tranches laid down in Article 49.1 of these Special Conditions are determined so that the retention sum amounts to 5% of the contract price at the moment of the Certificate of provisional acceptance.

47.2	By derogation to Article 47.2 of the General Conditions, the retention sums can be substituted by a retention guarantee.

Article 48	Price revision

48.1	Prices are fixed and shall not be revised.

Article 49	Measurement

49.1	This is a lump-sum contract.

Under the conditions imposed by the Special Conditions and General Conditions, the amounts due shall be calculated through the following tranches, expressed as percentage of the contract price:

|  | Percentage | Nature | Timing |
| --- | --- | --- | --- |
| 1. | 50% | Lump-sum advance of Article 46.1(a) | After finishing 50% of construction |
| … | 40% | Interim payment of Article 50 | After issuing of the Certificate of provisional acceptance |
| <last> | 10% | Retention money of Article 47 | Within 45 days of the issuing of the signed Final statement of account |

Article 50	Interim payments

50.7	The interim payments will be paid as determined in Article 49.1 of these Special Conditions.

Article 61	Defects liability

61.1	The defects liability period is defined as the period commencing on the date of provisional acceptance, during which the Contractor is required to make good any effect in, or damage to, any part of the work which may appear or occur during this period as notify by the Supervisor or the Contracting Authority. The rights and obligations of the parties with regard to this defects liability period are laid down in Article 61 of the General Conditions.

Article 68	Dispute settlement

68.4	All disputes will be settled at Economic Court Nis.

* * *